| **Risk Event** | **Probability** | **Consequences** | **Responsibility** | **Mitigation / Solution** | **Action by date** | **Outcome** |
| --- | --- | --- | --- | --- | --- | --- |
| Overcrowding - on the track risk of collision etc | Rare | Minor to Moderate | MAWA | * Monitor use with other training groups or visitors. * Laned races in outside lanes. | During the event | Efficient management of the resources and amenities available.  Comply with Event Management Permit |
| Dehydration | Moderate | Moderate | MAWA | * Encourage participants to bring water bottle * Public announcements to remain hydrated | Prior to and during the event | Participants remain hydrated, seek medical attention as required. |
| Heat / Sun stroke | Moderate | Moderate to severe | MAWA | * Public announcements to wear hats * Public announcements to wear sunscreen * Long run always last on hot evenings * Carefully watch athletes during long races for signs of stress, and force them to stop | Prior to and during the event | Public & athletes remain safe and well |
| MAWA member seriously injured or taken ill | Low | Major | MAWA | * Call ambulance * First aid administered * Ensure first aid kit is regularly checked and re-stocked | Prior to and during the event | Effective management/evacuation of casualties |
| MAWA member minor injury | Moderate | Minor | MAWA | * First aid administered | Prior to and during the event | Effective management  Minimise any potential serious casualties |
| Venue & competition area unsafe | Rare | Moderate | MAWA | * Inspect site prior to event for potential safety hazards | Prior to and during the event | No serious injuries to competitors |
| Competition – track events | Unlikely | Moderate | MAWA | * Inspect site prior to event for potential hazards * Officials ensure all equipment / hurdles etc are in the correct position * Ensure all IAAF rules are applied to ensure safety of competitors and officials * Allow access onto track arena only as required * First aid is available at every competition | Ongoing | No serious injuries to competitors and officials |
| Competition – field events | Unlikely | Moderate | MAWA | * Inspect site prior to event for potential hazards * No Hammer/Discus practice allowed outside of cages. * Ensure all weighted equipment is regularly checked by a qualified IAAF Technical official * Ensure all IAAF rules are applied to ensure safety of competitors and officials * Restrict unauthorised access onto field arena * First aid is available at every competition | On going | No serious injuries to competitors and officials |
| Non-arrival of the MAWA responsible person | Unlikely | Low | MAWA | * Ensure an alternate can be contacted to attend | Prior to the event | Efficient and effective management of the event |
| Electrical storm – lightning strike at ECAC | Unlikely | Major | MAWA | * Monitor weather forecast * Determine safety risk for staff and competitors * Provide adequate shelter for storage of property * Ensure adequate shelter for storage of electrical equipment * Suspend competition of it appears that storm will come close | Prior to and during the event | No person injured or harmed as a result of being struck by lighting |
| Inclement weather | Likely | Minor | MAWA | * Monitor weather forecast * Provide adequate shelter for storage of property * Ensure adequate shelter for storage of electrical equipment | Prior to and during the event | Event conducted with minimal disruption or discomfort |
| Disorderly conduct | Rare | Moderate | MAWA | * Assess then mediate or warn * Contact Police | On the day | Event conducted in a safe and friendly manner |
| Fire | Rare | Major | MAWA | * Familiarisation with procedures and evacuation routes | Prior to and during the event | No person injured.  Orderly evacuation of all persons |

**Key:**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Consequence** | | | | |
| Insignificant | Minor | Moderate | Major | Catastrophic |
|  | | | | |
| **Probability** | | | | |
| Rare | Unlikely | Moderate | Likely | Certain |